## Sheet1
RFSID | IssueType | Month | Flooding-O | Flooding_1 | Flooding_2 | Flooding_3 | Flooding_4 | Flooding_5 | Flooding_6 | Flooding_7 | Flooding_8
841179 | Flooding | 9 | 841179 | Roading - RR - Non Routine Maintenance | Sam Edlin | Drainage; e.g. Stormwater | Contractor Action and Completion | 19 | Sep | 2012 | (Sep 11 2012 10:59AM) XX Graham Street Whangamata Just a follow up call to XX conversation this morning regarding the ponding of water and poor drainage facilities outside our home at XX Graham Street. We have had owned the property for coming up
930385 | Flooding | 6 | 930385 | Roading - General Queries | Matt Lamb |  | Routine Maintenance - 5 Days | 18 | Jun | 2018 | (Jun 11 2018 10:52AM) XX of XX Chevron Crescent Whangamata has experienced large amounts of run off from the road which flooded his house - he is wanting to mitigate this by putting a grate drain on his driveway (he thinks it will be on his
918307 | Flooding | 12 | 918307 | Roading - Programmed Works | Pinnacles Civil |  | Programmable Works - 1 Month | 8 | Dec | 2017 | (Oct 30 2017 8:56AM) Attn: Thames Coromandel District Council (Group) A new RFS 740785 has been added with the following details: Category: Flooding - Roadside Ponding Customer: XX CustomerAddress: XX Ngati Porou Place, Whangamata Home Pho
908008 | Flooding | 3 | 908008 | Urban Road Open Drain | Veolia Water |  | Routine Maintenance - 5 Days New | 15 | Mar | 2017 | (Mar 8 2017 11:38AM) XX Ngati Pourou Whangamata - Stormwater drain blocked, severly, (Mar 10 2017 2:28PM) Closing with Note: part of all those advised to staff and dealt with among Emergency Flooding Event (our Job numbers W145295-99: one for each A
897595 | Flooding | 9 | 897595 | Roading - RR - Non Routine Maintenance | Opus Roading | Litter, Drain Channels, Espl Sand Bldup, Edge Mark | Customer Contact Initiated | 1 | Sep | 2016 | (Aug 11 2016 11:57AM) Can you please contact XX regarding stormwater runoff from Mooloo Crescent into the property causing damage. Their address is XX Mooloo Crescent Whangamata and contact no. is XX or XX. They wish
810647 | Flooding | 1 | 810647 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater Blk within Retic (Not due to heavy rain | Customer Contact Initiated | 15 | Apr | 2010 | (Apr 20 2010 1:49PM) Spoke with XX. She will send in photos of next flood. Added to Major Drainage List. XX (Apr 7 2010 10:32AM) Roadside flooding and catchpits are not United Water - please send to Roadiing. (Apr 15 2010 4:15PM) T
881714 | Flooding | 9 | 881714 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater Blockage - grate or catchpit | Customer Contact Initiated | 22 | Sep | 2015 | (Sep 7 2015 2:54PM) Inspected. Very little fines available - no action. Customer notified XX (Sep 1 2015 2:34PM) A new RFS 555573 has been added with the following details: Customer: XX CustomerAddress: XX Tamaki Road, Whangamata
899438 | Flooding | 10 | 899438 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater | Customer Contact Initiated | 14 | Oct | 2016 | (Sep 23 2016 12:32PM) XX who lives at XX Tobie Place, Whangamata has issues with stormwater runoff from the road onto his property. He would like to know if the stormwater from the road can be diverted along his ROW and onto the reserve at the r
840972 | Flooding | 9 | 840972 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater | Customer Contact Initiated | 12 | Sep | 2012 | (Sep 4 2012 1:41PM) XX , XX Riverview Rd WHANGAMATA ROADING- came in over the counter after a light rain to lay a complaint about all of the standing water along Riverview Rd. He believes there is a drainage problem as water is no
908037 | Flooding | 3 | 908037 | Urban Road Open Drain | Veolia Water |  | Routine Maintenance - 5 Days New | 15 | Mar | 2017 | (Mar 8 2017 3:39PM) A new RFS 686515 has been added with the following details: Customer: XX CustomerAddress: XXX McKeller Place, Whangamata Home Phone: (Unknown) Cell Phone: 027 404 2012 Work Phone: (Unknown) Fax: (Unknown) Email: (Unkno
835336 | Flooding | 3 | 835336 | Roading - RR - Non Routine Maintenance | Broadspectrum | Flooding | Contractor Action and Completion | 2 | Mar | 2012 | (Feb 23 2012 9:28AM) XX Aickin Road Whangamta - e-mail content as follows: After two recent rain events (fri 17th/mon 20th) the stormwater system in Aiken Rd failed to take all the water coming off the road,consequently the property at XX AIKEN Rd s
908032 | Flooding | 3 | 908032 | Urban Road Open Drain | Veolia Water |  | Routine Maintenance - 5 Days New | 15 | Mar | 2017 | (Mar 8 2017 3:11PM) XX Mckellar Place Whangamata open drain water overflowing and flooding the property XX Mckellar Place Whangamta has got into the sleep out has not reached the house yet (Mar 9 2017 10:45AM) We added this to the attn of XX,
838391 | Flooding | 6 | 838391 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater | Customer Contact Initiated | 6 | Jun | 2012 | (Jun 6 2012 2:07PM) Have spoken to XX. Will inspect this week. (Jun 13 2012 1:26PM) Have inspected. Left message for customer. We will not be doing anything. XX (May 28 2012 12:01PM) XX XX reported that in heavy rai
839336 | Flooding | 7 | 839336 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater | Customer Contact Initiated | 11 | Jul | 2012 | (Jul 11 2012 12:39PM) Investigating XX (Jul 18 2012 10:47AM) Visited XX. Told her landowner needs to upgrade their driveway and front berm. XX (Jul 3 2012 4:33PM) Stormwater run-off from Graham Street Whangamata is being
913400 | Flooding | 7 | 913400 | Roading - RR - Non Routine Maintenance | Sam Edlin |  | Customer Contact Initiated | 5 | Jul | 2017 | (Jun 27 2017 2:31PM) XX Saint Patricks Row Whangamata - has had ongoing issues of stormwater pooling at the end of the cul de sac and then it spills into their property and then they have to get insurance company to replace damaged gib etc etc. Please
816103 | Flooding | 11 | 816103 | Roading - RR - Programable Works - 2 Months | Broadspectrum | Stormwater | Programmable Works - 2 Months | 30 | Nov | 2010 | (Dec 23 2010 9:11AM) NTC 283 for Februry programme XXX (Oct 12 2010 12:02PM) To investigate XX (Oct 18 2010 11:58AM) NTC 251 to be reviewed XX (Oct 19 2010 9:41AM) NTC 251 for November programme to fill low area to
929979 | Flooding | 6 | 929979 | Flooding Private Land | Matt Lamb |  | Field Rep Decision | 6 | Jun | 2018 | (Jun 5 2018 12:56PM) XX Barbara Avenue Whangamata XX - XX Would like someone to look at the stormwater on Barbara Avenue please. With the heavy rain on the weekend the water came through his neighbours property onto XX section, leve
910494 | Flooding | 5 | 910494 | Sports ground - Field Maintenance/Turf Renovations | Lou Mackwell |  | Contractor Action and Completion | 8 | May | 2017 | (Apr 21 2017 3:31PM) Would like feedback. Thanks (Apr 21 2017 3:14PM) The property at XX Aickin Road Whangamata flooded in March - she is going to get her stormwater drainage looked at but would also like the rugby ground and netball courts looked a
910097 | Flooding | 1 | 910097 | Flooding Private Land | Julie Dennis |  | Routine Maintenance 1 Day - NEW | 18 | Apr | 2017 | (Apr 18 2017 9:36AM) A new RFS 697205 has been added with the following details: Customer: XX CustomerAddress: New Zealand Home Phone: XX Cell Phone: XX Work Phone: Central -XX: (Unknown)
812652 | Flooding | 6 | 812652 | Roading - RR - Routine Maintenance - 1 Day | Broadspectrum | Flooding |  | 2 | Jun | 2010 | (Jun 2 2010 12:08PM) Attended twice yesterday - cleared cesspite but there appears to be a cable running through the pipe that cuts capacity of drainage (Jun 1 2010 12:26PM) XX from XX Pipi Road, Whangamata - Phoen XX has advised that
908030 | Flooding | 3 | 908030 | Urban Road Open Drain | Veolia Water |  | Routine Maintenance - 5 Days New | 15 | Mar | 2017 | (Mar 8 2017 3:00PM) A new RFS 686513 has been added with the following details: Customer: Fields, XX CustomerAddress: mcKellar Place, Whangamata Home Phone: (Unknown) Cell Phone: (Unknown) Work Phone: (Unknown) Fax: (Unknown) Email: (Unknown)
930178 | Flooding | 6 | 930178 | Roading - General Queries | Matt Lamb |  | Routine Maintenance - 5 Days | 13 | Jun | 2018 | (Jun 6 2018 1:59PM) kiwi road whangamata - customers property has flooded very badly again - coming from kiwi road and williamson road - drain across from her property she said goes nowhere - she said the cesspits were cleaned out about 6 weeks ago
914342 | Flooding | 7 | 914342 | Flooding Private Land | Andy Thrush |  | Routine Maintenance 1 Day - NEW | 21 | Jul | 2017 | (Jul 20 2017 2:48PM) XX Governors heights Whangamata - XX from this address came in today regarding the stream and stormwater on her property - after the march event her property was under 4 foot of water. Someone from TCDC was out there and also th
934991 | Flooding | 9 | 934991 | Ponding Private Land | Matt Lamb |  | Field Rep Decision | 27 | Sep | 2018 | (Sep 25 2018 1:27PM) Spoke with XX at 1:20pm. I discussed with XX steps she may wish to take as the water in the photos is in the same areas as her soakage cells. i explained that they would require maintenance and this may help to relieve some of
823730 | Flooding | 3 | 823730 | Roading - RR - Non Routine Maintenance | Opus Roading | Customer Complaint | Customer Contact Initiated | 29 | Mar | 2011 | (Mar 21 2011 11:22AM) , XX, XX Philomel Road, Whangamata Philomel Road has recently been graded. they have always had trouble with water outside their property when it rains. Now its not just puddles its a lake! Would like someone to have a loo
835251 | Flooding | 2 | 835251 | Roading - RR - Non Routine Maintenance | Eileen Hopping | Customer Complaint | Contractor Action and Completion | 29 | Feb | 2012 | (Feb 21 2012 10:02AM) XX Port Road Whangamata - XX - during heavy rain water (rainwater) is being channelled onto the property from the road - can this please be investigate and fixed before winter - Photo has been supplied (Feb 23 2012 1
895898 | Overflow | 7 | 895898 | Stormwater -Routine Maintenance - 1 Day | Veolia Water | Manhole Cover - SW or WW | Routine Maintenance 1 Day - NEW | 5 | Jul | 2016 | (Jul 6 2016 2:55PM) Checked no blockage caused to lift. Due to heavy rain. Reinstated. - 4 July. (Jul 4 2016 10:09AM) XX from XX Tirohanga Drive, Whangamata has called to advise that the manhole cover needs to be reinstated outside their
812799 | Flooding | 6 | 812799 | Roading - RR - Non Routine Maintenance | Suzanne Cook | Gen P & R Mtce, Bldgs, Cems, Carparks, Boatramps | Customer Contact Initiated | 15 | Jun | 2010 | (Jun 16 2010 1:23PM) XX, Have spoken with property owner and confirmed this is a roading issue - flooding is caused by lack of K&C, and not due to truck parked on RR. (Jun 24 2010 1:29PM) Investigating XX (Jul 2 2010 9:27AM) Have
871696 | Flooding | 1 | 871696 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater | Customer Contact Initiated | 13 | Jan | 2015 | (Dec 23 2014 8:09AM) Have been to site and talked to XX. His driveway-section is lower than the road. New roadworks has not supplied enough drainage as Council has limited funds. Will put in Major Drainage List for kerb and channel or soakhole. Bre
930439 | Flooding | 6 | 930439 | Parks and Reserves Non-Routine | Lou Mackwell |  | Contractor Action and Completion | 25 | Jun | 2018 | (Jun 11 2018 4:18PM) Please fill and place sandbags against the garages and doorways of XX & XX Esplanade Drive Whangamata as instructed by XX, XX. (Jun 15 2018 12:11PM) Dayworks approved . I will check with XX that this was done (J
909240 | Flooding | 1 | 909240 | General Service Query | Andy Thrush |  | Asset Manager Approval | 6 | Apr | 2017 | (Mar 30 2017 10:48AM) XX Williamson Road Whangamata - flooding obviously occurred in the big flood but everytime it rains now the lawn and garden flood quite badly - thinks its from the williamson park stormwater lake not flowing and the water table be
814067 | Flooding | 7 | 814067 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater | Customer Contact Initiated | 27 | Jul | 2010 | (Jul 19 2010 11:52AM) XX & XX Port Road Whangamata - stormwater runoff from the road is running into these properties - the worst one being XX and the water is pooling under the houses and is rotting out some of the baseboards. (Jul 27 2010 12:50P
909519 | Flooding | 1 | 909519 | Assess Stormwater Maintenance | Broadspectrum |  | Routine Maintenance - 2 Days | 6 | Apr | 2017 | (Apr 5 2017 10:01AM) Attn: Thames Coromandel District Council (Group) A new RFS 693888 has been added with the following details: Customer: XX Address: XX Williamson Road, Whangamata Home Phone: XX Cell Phone: (Unknown
810711 | Flooding | 1 | 810711 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater | Customer Contact Initiated | 15 | Apr | 2010 | (Apr 7 2010 3:57PM) Ocean Road Whangamata - the stormwater drain outside this property did not cope with the downpour last night 06.04.10 with houses nearly getting flooded. Not sure if the cesspit is blocked or the pipes aren't big enough, or if
930203 | Flooding | 6 | 930203 | Roading - General Queries | Matt Lamb |  | Routine Maintenance - 5 Days | 13 | Jun | 2018 | (Jun 6 2018 2:38PM) N.B. PREVIOUS RFS WAS COMPLETED AS CATCHPITS WERE FINE From: XX [mailto: XX@XX.org.nz] Sent: Tuesday, 5 June 2018 4:33 p.m. To: TCDC General Mail Address Subject: XX Ocean Road Whangamata good Afternoon We c
872058 | Flooding | 1 | 872058 | Roading - RR - Programable Works - 1 Month | Broadspectrum | Litter, Drain Channels, Espl Sand Bldup, Edge Mark | Programmable Works - 1 Month | 28 | Jan | 2015 | (Dec 24 2014 2:02PM) XX Kiwi Road Whangamata - there is a large depression alongside this road and in heavy rain the water builds up and causes surface water to flood onto the road. This occurs all along Kiwi Road but is more of an issue outside some
909472 | Flooding | 1 | 909472 | Assess Stormwater Maintenance | Broadspectrum |  | Routine Maintenance - 2 Days | 6 | Apr | 2017 | (Apr 4 2017 9:59AM) The owner of XX Mary Road Whangamata came into the area office yesterday concerned about the surface water that is not receding - house was flooded last time and with the impending rain it is bound to flood again. A lot coming fro
926491 | Flooding | 1 | 926491 | General Service Query | Andy Thrush |  | Field Rep Decision | 3 | Apr | 2018 | (Apr 4 2018 7:35AM) Hi XX I just had this one sent to me after it was initially directed to someone else. can you follow up pelase (Mar 23 2018 2:01PM) Hi Team Customer came into counter at the end of last year after the big storm where Whangamat
825490 | Flooding | 5 | 825490 | Roading - RR - Routine Maintenance - 1 Day | Broadspectrum | Flooding |  | 9 | May | 2011 | (May 9 2011 9:44AM) XX Hetherington Road, Whangamata. Backloaded afterhours RFS 06/05/11 5.22pm. Please call as my home is flooding from council water. ****** ACTIVITIES ****** 1) 05-06 05:25PM XX XX) 05-06 05:27PM V
871755 | Flooding | 12 | 871755 | Stormwater -Routine Maintenance - 5 Days | Rachel Ludemann | Stormwater | Routine Maintenance - 5 Days New | 29 | Dec | 2014 | (Dec 18 2014 1:00PM) Is flowing. Did ink check test. Was just volume from the deluge. (Dec 18 2014 10:06AM) XX who lives at XX Hetherington Road, Whangamata has asked if we can please check the stormwater drain behind her property (this is a
909844 | Flooding | 1 | 909844 | Assess Stormwater Maintenance | Broadspectrum |  | Routine Maintenance - 2 Days | 12 | Apr | 2017 | (Apr 10 2017 3:48PM) XX fom XX Bellona Road, Whangamata, has requested that the drain that is in front of XX Bellona Road be cleared please as he said that in heavy rain the road floods from Williamson Road to his property. (Apr 12 2017
908305 | Flooding | 3 | 908305 | General Service Query | Veolia Water |  | Asset Manager Approval | 20 | Mar | 2017 | (Mar 13 2017 3:28PM) XX Linton Crescent Whangamata - Customer called in to say they travelled over to check on property. they filled two large sink holes on property driveway. They want to report that the sink holes were over a Council stormwater easem
910488 | Flooding | 5 | 910488 | General Queries - Non Routine | Opus Roading |  | Customer Contact Initiated | 15 | May | 2017 | (Apr 21 2017 2:56PM) XX Bellona Road Whangamata - I have visited the site and the water is pretty stagnant and pooling. The drain accross the road at XX Bellona Road is not draining and also needs investigation. Please communicate back with customer.
948673 | Overflow | 6 | 948673 | Manhole | Veolia Water |  | Routine Maintenance 1 Day - NEW | 7 | Jun | 2019 | (Jun 6 2019 1:46PM) Can you please advise why this has been sent back to my colleague in Customer Services. I have checked the TCDC Smart Maps and this is a utilities asset - Asset ID 101,211. Can the lid please be reinstated asap. Thank you (Jun 6 2
910509 | Flooding | 1 | 910509 | Assess Road and Bridge Maintenance | Broadspectrum |  | Routine Maintenance - 2 Days | 26 | Apr | 2017 | (Apr 24 2017 8:31AM) Attn: Thames Coromandel District Council (Group) A new RFS 700163 has been added with the following details: Customer: XX CustomerAddress: XX Bellona Road, Whangamata Home Phone: (Unknown) Cell Phone: XX Work P
932677 | Flooding | 8 | 932677 | Roading - RR - General Service Query | Matt Lamb |  | Asset Manager Approval | 17 | Aug | 2018 | (Apr 16 2019 3:06PM) Our water services team have a consultant looking into the overall function of the stormwater system in Whangamata. This area is lowlying and relies on soakage which is limited during large rainfall events. (Aug 2 2018 2:49PM) Pre
797481 | Flooding | 1 | 797481 | Roading - RR - Non Routine Maintenance | Opus Roading | Flooding | Customer Contact Initiated | 8 | Apr | 2009 | (Mar 31 2009 4:39PM) XX , XX Beach Road Whangamata Has been dealing with XX in trying to get a flooding issue resolved at his place. Has caused much grief and has been told that the drainage was poor and incificiant and that the
889538 | Flooding | 3 | 889538 | Roading - RR - Routine Maintainence - 10 Days | Broadspectrum | Stormwater Blockage - grate or catchpit | Routine Maintenance 1 Day - NEW | 4 | Mar | 2016 | (Feb 19 2016 12:02PM) Attended Site. Roading issue - please refer to Broadspectrum (Transfield) (Mar 1 2016 4:38PM) Cesspit has been cleared. BRS TB (Feb 19 2016 10:51AM) Outside XX Beach Road, Whangamata the stormwater drain is blocked. Its overf
890138 | Flooding | 3 | 890138 | Roading - RR - Routine Maintainence - 10 Days | Broadspectrum | Stormwater | Routine Maintenance - 10 Days | 11 | Mar | 2016 | (Mar 3 2016 9:27AM) Dealt with under 889538. Cesspits clear. Opus making decision on outlet at the beach. BRS TB (Mar 1 2016 2:13PM) A new RFS 601165 has been added with the following details: Customer: XX CustomerAddress: XX Beach Roa
855531 | Flooding | 11 | 855531 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater Blockage - grate or catchpit | Customer Contact Initiated | 27 | Nov | 2013 | (Dec 17 2013 1:42PM) recommendation is that this go in the Major Drainage List XX (Nov 13 2013 8:37AM) Investigating XX (Dec 3 2013 8:33AM) Investigating and will report options for inclusion in drainage programme. Issue will
797454 | Flooding | 1 | 797454 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater | Contractor Action and Completion | 8 | Apr | 2009 | (Mar 31 2009 11:56AM) XX Achilles Ave Whangamata - stormwater flooding, problem still has not been solved, photos were sent to XX August last year, customers basement, sleepout carpets are damaged everytime there is heavy rain as there is only
835098 | Flooding | 2 | 835098 | Roading - RR - Non Routine Maintenance | Opus Roading | Flooding | Customer Contact Initiated | 27 | Feb | 2012 | (Feb 17 2012 9:18AM) XX Achilles Avenue Whangamata - the stormwater runoff from the road is flooding his property and he wants someone to go and look at it now because this has been happening for the last 5 years (Feb 27 2012 11:25AM) Investigating XX
808224 | Flooding | 2 | 808224 | Roading - RR - Routine Maintenance - 1 Day | Broadspectrum | Stormwater Blockage - grate or catchpit |  | 2 | Feb | 2010 | (Feb 2 2010 10:44AM) XX Achilles Avenue, Whangamata. Backloaded afterhours RFS 01/02/10 10.31am. Surface flooding from road onto property. 11.02am - pass mob XX (Feb 8 2010 3:50PM) Full tide corresponding with heavy rain prevented surface water
796320 | Flooding | 3 | 796320 | Roading - RR - Routine Maintenance - 1 Day | Broadspectrum | Flooding |  | 2 | Mar | 2009 | (Mar 2 2009 10:50AM) XX of our Thames depot attended. Cesspits and drains were all checked for blockages but nothing found. Seems to be a re-curring problem for this home-owner when there is heavy rain. House did not flood. (Mar 6 2009
933510 | Flooding | 8 | 933510 | Flooding Private Land | Andy Thrush |  | Routine Maintenance 1 Day - NEW | 22 | Aug | 2018 | (Aug 22 2018 9:38AM) REF RFS #932603 (Aug 22 2018 8:18AM) From: XX <XX@gmail.com> Date: 21 August 2018 at 15:48:56 NZST To: customer.services@tcdc.gov.nz Subject: Att. Of mr. XX Hello XX , Here a few photos of the situat
908983 | Flooding | 3 | 908983 | General Service Query | Veolia Water |  | Contractor Action and Completion | 31 | Mar | 2017 | (Mar 24 2017 2:08PM) The owner of Ocean Road Whangamata came in the area office today regarding the roading asset outside his property (ID no. XX) - his house flooded in the big flood two weeks ago but says the issue is the williamson park sto
930094 | Flooding | 6 | 930094 | Flooding Public Land | Veolia Water |  | Routine Maintenance 1 Day - NEW | 5 | Jun | 2018 | (Jun 5 2018 3:12PM) Attn: Thames Coromandel District Council (Group) A new RFS 808273 has been added with the following details: Category: Flooding - Public Land Customer: XX CustomerAddress: XX Ocean Road, Whangamata Home Phone: (Unkn
825636 | Flooding | 5 | 825636 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater | Customer Contact Initiated | 20 | May | 2011 | (May 12 2011 8:19AM) Port Rd WHANGAMATA Roading- During rain stormwater is inundating the rear of the property from the ROW. Please investigate and make necessary repairs. Please liase with XX about the job as he will be undertaking any
812668 | Flooding | 6 | 812668 | Stormwater -Non Routine Maintenance | Darren Teulon | Flooding | Contractor Action and Completion | 10 | Jun | 2010 | (Jun 10 2010 8:48AM) Please redirect to TCDC Utilities to note for SW upgrade - inadequate system. Will place XX on Major Drainage List but SW system needed first. XX (Jul 5 2010 4:10PM) CCTV completed. Some minor root intrusion at j
808572 | Flooding | 3 | 808572 | Roading - RR - Programable Works - 1 Month | Broadspectrum | Stormwater Blockage - grate or catchpit | Programmable Works - 1 Month | 9 | Mar | 2010 | (Feb 16 2010 1:27PM) Work to be programmed and or cyclic work. Letter sent to XX. XX (Feb 16 2010 2:33PM) This item will be put into our April programme to be submitted 20.03.10. Please extend to mid April to submit, optai
810281 | Flooding | 1 | 810281 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater | Customer Contact Initiated | 5 | Apr | 2010 | (Mar 26 2010 4:00PM) Beach Road Whangamata - surface water flowing in off road and flooding bottom unit. Can on-site meeting with XX as soon as possible. Thanks (Apr 7 2010 8:45AM) To meet customer on site (Apr 13 2010 8:28AM) Hav
909326 | Flooding | 1 | 909326 | Assess Stormwater Maintenance | Broadspectrum |  | Routine Maintenance - 2 Days | 4 | Apr | 2017 | (Mar 31 2017 12:24PM) A lot of Bellona Road Whangamata - the stormwater isn't draining away - driveways are turning to mud. It may need to be looked into. (Apr 10 2017 8:08AM) Water is draining away now that the rain has stopped.RM/BRS.
796353 | Flooding | 3 | 796353 | Roading - RR - Routine Maintenance - 1 Day | Broadspectrum | Flooding |  | 2 | Mar | 2009 | (Mar 2 2009 11:39AM) Chartwell Avenue, Whangamata. Backloaded after hours RFS 28/02/09 8.13am. Road severely flooding into properties 8.27am - pass mob XX
835106 | Flooding | 2 | 835106 | Water - Routine Maintenance - 5 Days | Veolia Water | Gutters | Routine Maintenance - 5 Days | 24 | Feb | 2012 | (Feb 17 2012 10:29AM) Chartwell Avenue Whangamata - the Cnr of Chartwell Avenue is flooded and has flooded 3 properties, please check (Feb 17 2012 11:52AM) XX has just rung in and its all clear and water has disspated - deluge was that great the storm
840437 | Flooding | 9 | 840437 | Roading - RR - Programable Works - 1 Month | Broadspectrum | Stormwater Blockage - grate or catchpit | Programmable Works - 1 Month | 11 | Sep | 2012 | (Aug 14 2012 2:16PM) Cnr Graham Street/Bellona Road Whangamata - please check and maintain the soak holes in this area as there is severe flooding - photos have been put into dataworks (Aug 28 2012 10:29AM) NTC 457 for review. Left message for XX.
804797 | Overflow | 11 | 804797 | Roading - RR - Non Routine Maintenance | Broadspectrum | Stormwater | Customer Contact Initiated | 20 | Nov | 2009 | (Nov 12 2009 1:57PM) Harry Watt Drive Whangamata - on the road reserve just before Ngati Pourou Place there is a cesspit that the grate is half open on - the cess pit is full of water - the customer tried to put the grate back down but the whole thing r
844843 | Flooding | 1 | 844843 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater | Customer Contact Initiated | 10 | Jan | 2013 | (Dec 31 2012 3:15PM) Hinemoa Street Whangamata - please refer to RFS 839662 - XX came into the office and something needs to be done about the stormwater not getting away - for 3 days people could not access the beach access as the water was over
846672 | Flooding | 2 | 846672 | Roading - RR - Non Routine Maintenance | Opus Roading | Stormwater | Customer Contact Initiated | 13 | Feb | 2013 | (Feb 5 2013 1:43PM) Same issue and person as RFS 844843. XX has been rung. XX (Feb 4 2013 2:33PM) Please change to non routine and re direct to Opus (XX). (Refer to previous RFS 839662 for background info) Thanks XX (Feb 4
909995 | Flooding | 1 | 909995 | Assess Stormwater Maintenance | Broadspectrum |  | Routine Maintenance - 2 Days | 18 | Apr | 2017 | (Apr 13 2017 8:37AM) Attn: Thames Coromandel District Council (Group) A new RFS 696457 has been added with the following details: Customer: XX CustomerAddress: XX Port Road, Whanagmata Home Phone: XX Cell Phone: (Unknown) Work Pho
908034 | Flooding | 3 | 908034 | Assess Stormwater Maintenance | Broadspectrum |  | Routine Maintenance - 2 Days | 10 | Mar | 2017 | (Mar 8 2017 3:21PM) A new RFS 686530 has been added with the following details: Customer: XX CustomerAddress:New Zealand Work Phone:XX Home Phone:XX Cellphone: XX Fax:(Unknown) Emai
812675 | Flooding | 6 | 812675 | Roading - RR - Routine Maintenance - 1 Day | Broadspectrum | Flooding |  | 2 | Jun | 2010 | (Jun 2 2010 12:15PM) Attended twice and cleared twice (Jun 1 2010 3:32PM) Island View Road - Pipi Road, Whangamata Is flooded completely because of blocked drains. Reported by XX phone XX Please investigate and attend as soon as you c
814422 | Flooding | 8 | 814422 | Roading - RR - Routine Maintenance - 1 Day | Broadspectrum | Stormwater Blockage - grate or catchpit |  | 3 | Aug | 2010 | (Aug 3 2010 8:51AM) Cyclic crew have inspected drain and found it to be just a soak hole as are many others in Whangamata. No blockage and water has now dissipated. Problem common in Whangamata during heavy rain as there is little kerb and channeling
883231 | Flooding | 10 | 883231 | Roading - RR - Routine Maintenance - 2 Days | Broadspectrum | Stormwater Blockage - grate or catchpit | Routine Maintenance - 2 Days | 16 | Oct | 2015 | (Oct 19 2015 9:50AM) This is a new soak hole it is not blocked it just fills up after the heavy rain pour. XX (Oct 14 2015 9:23AM) XX has called to advise of a blockage in the stormwater drain approximately 2/3rds of the way down Kiwi Roa
903698 | Overflow | 12 | 903698 | Manhole | Veolia Water |  | Routine Maintenance 1 Day - NEW | 19 | Dec | 2016 | (Dec 19 2016 9:47AM) Attn: Thames Reticulation (Group) A new RFS 663706 has been added with the following details: Customer: XX CustomerAddress: Port Road and Ocean Road, Whangamata Home Phone: (Unknown) Cell Phone: (Unknown) Work Phone: XX
899482 | Flooding | 10 | 899482 | Roading - RR - Non Routine Maintenance | Opus Roading | Litter, Drain Channels, Espl Sand Bldup, Edge Mark | Customer Contact Initiated | 17 | Oct | 2016 | (Sep 26 2016 11:10AM) End of Mooloo Cres Whangamata flooding - this is an ongoing issue and is becoming a regular hassle. Can this please be investigated and sorted please. Thanks XX (Sep 26 2016 11:11AM) Ongoing issue - refer XX (S
814322 | Overflow | 7 | 814322 | Stormwater -Routine Maintenance - 2 Days | Veolia Water | Manhole Cover - SW or WW | Routine Maintenance - 2 Days | 30 | Jul | 2010 | (Jul 28 2010 9:18AM) A stormwater manhole has popped its lid and needs to be reseated. It is located at the northern end of the walkway between Given Ave/Mary Road and Ocean Road and Whangamata - near the intersection of Ocean Road and Rangi Road (Jul
796352 | Flooding | 3 | 796352 | Roading - RR - Routine Maintenance - 1 Day | Broadspectrum | Flooding |  | 2 | Mar | 2009 | (Mar 2 2009 11:33AM) Ocean Road, Whangamata. Backloaded afterhours RFS 28/02/09 8.07am. Severe flooding 8.26am - pass mob XX (Mar 3 2009 9:15AM) Investigated as RFS 796320. Cesspits and drains checked and no cause could be found.
812650 | Flooding | 6 | 812650 | Roading - RR - Non Routine Maintenance | Opus Roading | Flooding | Customer Contact Initiated | 10 | Jun | 2010 | (Jun 3 2010 11:06AM) Will now be handled under RFS 812672 XX (Jun 3 2010 11:00AM) See RFS 812672 response (Jun 1 2010 1:05PM) Our crew attended this issue as soon as it came in but unfortunately could not halt the flooding. They checked the dr
930405 | Flooding | 6 | 930405 | General Service Query | Veolia Water |  | Contractor Action and Completion | 18 | Jun | 2018 | (Jun 11 2018 2:57PM) Hi XX, can you have a look at this one in the first instance XX (Jun 11 2018 1:12PM) LETTERS AND PHOTOS ATTACHED IN ECM - DOC SET NO. 5414474 - the 3 waters maps indicate this is mainly utilities. From: patfin [patfin@orco
823295 | Flooding | 3 | 823295 | Stormwater -Non Routine Maintenance | Veolia Water | Drainage; e.g. Stormwater | Contractor Action and Completion | 16 | Mar | 2011 | (Mar 8 2011 12:35PM) Park Avenue Reserve Whangamata - as per letter in dataworks - no. 2093942 - there has been flood damage to the open drain that runs the length of the reserve which has also caused subsidence in the few places so that the concrete ed
812666 | Flooding | 6 | 812666 | Stormwater -Non Routine Maintenance | Evan Vaughters | Stormwater Blockage - grate or catchpit | Contractor Action and Completion | 10 | Jun | 2010 | (Jun 3 2010 12:07PM) Please redirect and change code to TCDC Utilities for future SW upgrade works. My comments - Phoned customer. He confirms water came back up out the cesspits and took about 60 seconds to reach the shop floor level. A depth of 300m
911253 | Flooding | 5 | 911253 | General Queries - Non Routine | Opus Roading |  | Customer Contact Initiated | 29 | May | 2017 | (May 8 2017 3:01PM) DOC SET NO. 4805143 From: XX [XX@gmail.com] Sent: Sunday, May 07, 2017 6:35:36 PM To: TCDC General Mail Address Subject: Sylvia Road still soggy from storms Hi there I am wondering if there is any particular
814115 | Overflow | 7 | 814115 | Stormwater -Routine Maintenance - 1 Day | Veolia Water | Manhole Cover - SW or WW |  | 21 | Jul | 2010 | (Jul 20 2010 10:06AM) The Drive Whangamata - the manhole just below where Fernleigh Road joins The Drive - the lid has lifted and is sitting skew whiff on the top - can this be seen to a.s.a.p. before a car hits it and causes some damage - thank you (Jul
895782 | Flooding | 6 | 895782 | Roading - RR - Routine Maintenance - 1 Day | Broadspectrum | Stormwater Blockage - grate or catchpit | Routine Maintenance - 1 Day | 30 | Jun | 2016 | (Jun 29 2016 5:15PM) XX has called to advise that stormwater has flowed from a sub-division on SH25, across the state highway, down Widdison Place, down her driveway and into her garage and under her front door. She is extremely upset as the
912731 | Flooding | 6 | 912731 | General Service Query | Ian Smith |  | Asset Manager Approval | 16 | Jun | 2017 | (Jun 19 2017 12:00PM) XX responded to Whangamata Ratepayers Association. See doc set 4866873. (Jun 16 2017 3:51PM) XX responded to XX see doc set 4864215. (Jun 9 2017 1:30PM) DocSet# 4854385 8TH JUNE 2017 REQUEST FOR SERVICE WILL
814079 | Overflow | 7 | 814079 | Stormwater -Routine Maintenance - 1 Day | Veolia Water | Manhole Cover - SW or WW |  | 19 | Jul | 2010 | (Jul 19 2010 1:53PM) Williamson Road, Whangamata. Backloaded afterhours RFS 17/07/10 9.51am. Manhole cover popped up due to heavy rain, lid is up on a tilt (opposite Bell Street) Pager ID XX (Jul 23 2010 11:43AM) Replaced manhole lid correctly.
931704 | Flooding | 7 | 931704 | General Service Query | Karen Steffek |  | Asset Manager Approval | 19 | Jul | 2018 | (Jul 12 2018 1:56PM) Hi XX This just got fired through to me Have we had any correspondance with these owners since Queens Birthday? Just trying to understand if its an issue you have already dealt with or if we need to speak to them regarding wha
912274 | Flooding | 5 | 912274 | Flooding a Building | Andy Thrush |  | Routine Maintenance 1 Day - NEW | 31 | May | 2017 | (May 30 2017 1:46PM) XX ph XX of XX Williamson Road Whangamata phoned to voice she was concerned nothing was being done about the flooding in Williamson road concerning her property. When asked to explain she has been flooded once in the ea